AGS3D

Prototype Task List

Structured task breakdown for the minimum viable prototype  |  2026

Prototype success criterion: a single AGS-spirit script transpiles to GDScript, a room with basic logic geometry loads in Godot, a character walks to a named point referenced by name in script, and the result runs correctly end to end. No dialogue, no inventory, no save system.

| Milestone | Tasks | Primary Risk | Input | Output |
| --- | --- | --- | --- | --- |
| M1 — Godot Fork Setup | T01–T05 | Low | Godot source | Clean fork with module structure |
| M2 — AGS-Spirit Parser | T06–T12 | High | Language spec | AST from .agscript files |
| M3 — GDScript Emitter | T13–T18 | Med | AST (M2) | Valid runnable GDScript |
| M4 — Room Node | T19–T24 | Med | Godot fork (M1) | Room with logic geometry in editor |
| M5 — Character Node | T25–T29 | Med | Room node (M4) | Character that navigates the room |
| M6 — End-to-End Wiring | T30–T36 | High | M2+M3+M4+M5 | Script drives character in room |

MILESTONE 1 Godot Fork Setup Establish the fork, module skeleton, and build pipeline before any engine code is written

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T01 | Fork Godot and establish repository - Fork official Godot repo on GitHub - Set upstream remote for future merges - Confirm clean build on target dev platform | Clean build passes on dev machine. CI pipeline builds the fork on push. | — | Low |
| T02 | Create module skeleton: modules/agvm/ - Create modules/agvm/ directory with SCsub - Register module in build system - Add stub class that prints on engine init | Engine boots and stub log line appears confirming module is loaded. | T01 | Low |
| T03 | Register AGS-spirit ScriptLanguage interface - Implement ScriptLanguage subclass: AGSScriptLanguage - Register with ScriptServer in module init - Stub all required virtual methods | Godot editor recognises .agscript as a known file type. No functionality yet. | T02 | Low |
| T04 | Define project file format and scanner - Define game.agp TOML schema - Implement directory scanner that finds all .agscript, .agroom, .agchar files - Implement scanner and project model in Go (tools/ag/internal/project/) | Scanner correctly enumerates all adventure game source files from a minimal test project directory. | T02 | Low |
| T05 | Build pipeline: ag CLI stub - Create ag command-line tool - Implement ag build (stub, just prints plan) - Implement ag run (launches Godot with project path) | ag run launches the Godot editor with the test project loaded. | T01 | Low |

MILESTONE 2 AGS-Spirit Parser Parse AGS-spirit source files into a well-formed AST — this is the highest-risk milestone

This is the hardest milestone. The parser and AST are the foundation everything else builds on. Invest in correctness and good error messages here — they pay dividends across the entire project.

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T06 | Define the AGS-spirit grammar (formal spec) - Document supported subset of AGS Script syntax - Specify: functions, variables, if/else, while, return - Specify: event handlers (room_Enter, hotspot_Interact, etc.) - Specify: built-in type names (Character, Room, Point, Region) - Explicitly list what is NOT supported in prototype scope | Written grammar spec document exists before any parser code is written. Scope is deliberately minimal. | — | Med |
| T07 | Implement lexer / tokenizer - Token types: keywords, identifiers, literals, operators, punctuation - Line and column tracking for error messages - Skip whitespace and comments correctly | Lexer correctly tokenizes all constructs defined in the grammar spec. Unit tests cover all token types. | T06 | Med |
| T08 | Define AST node types - FunctionDecl, EventHandler, Block, IfStmt, WhileStmt - AssignStmt, ReturnStmt, ExprStmt - CallExpr, MemberExpr, BinaryExpr, UnaryExpr - Literal (int, float, string, bool), Identifier | AST node hierarchy defined in code with clear ownership semantics. No parsing yet. | T06 | Low |
| T09 | Implement recursive descent parser - Parse function declarations and event handler blocks - Parse all statement types from grammar spec - Parse expressions with correct precedence - Build AST nodes from parsed constructs | Parser correctly produces AST for a representative set of AGS-spirit scripts. All grammar spec constructs handled. | T07, T08 | High |
| T10 | Implement symbol table and type resolver - First pass: collect all function and variable declarations - Second pass: resolve all identifier references - Validate that referenced names exist - Record type of each expression node | Symbol table correctly resolves all names in test scripts. Undefined references produce clear error messages with file and line number. | T09 | Med |
| T11 | Identify and annotate blocking calls - Maintain list of known blocking built-in functions (WalkTo, PlayAnimation, Wait, etc.) - During symbol resolution, annotate all call sites to blocking functions - Mark containing function as async if it contains any blocking call | All blocking call sites correctly annotated in the AST. Needed by emitter to insert await correctly. | T10 | Med |
| T12 | Parser error handling and recovery - Produce actionable error messages: file, line, column, what was expected vs found - Implement basic panic-mode recovery to continue parsing after errors - Never crash on malformed input — always produce an error list | Parser handles all malformed inputs in test suite without crashing. Error messages are clear enough to act on without reading parser source. | T09 | Med |

MILESTONE 3 GDScript Emitter Walk the AST and emit valid, readable GDScript that Godot can execute

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T13 | Implement emitter scaffolding - AST visitor pattern or recursive walk function - Output buffer with indentation tracking - File writer that places output in .engine/generated/ | Emitter scaffolding in place. Can be invoked on an AST and produces an (empty) output file. | T09 | Low |
| T14 | Emit function and event handler declarations - Map AGS-spirit function names to GDScript func - Map event handler names to Godot signal handler naming convention - Emit function signatures with correct parameter lists | Function and event handler skeletons emit correctly. GDScript parser accepts output. | T13 | Low |
| T15 | Emit statements and expressions - All statement types: if/else, while, assign, return, expr - All expression types: call, member access, binary, unary, literal, identifier - Correct GDScript operator mapping | All constructs from grammar spec emit correct GDScript. Round-trip test: parse then emit simple scripts and confirm GDScript is valid. | T13, T14 | Med |
| T16 | Emit blocking calls with await - For each annotated blocking call site, emit await keyword before the call - For async-marked functions, emit async func signature in GDScript - Verify await chains correctly through multiple call levels | character.WalkTo(point.door) in AGS-spirit emits await character.walk_to(point_door) in GDScript. Walk completes before next line executes. | T11, T15 | High |
| T17 | Emit source map file - For each emitted GDScript line, record the originating AGS-spirit file and line - Write source map as a sidecar .agmap file alongside generated GDScript - Source map format: simple JSON array of [gdscript_line, agscript_file, agscript_line] | Source map covers all emitted lines. Manual verification: a known AGS-spirit line maps to the correct GDScript line. | T15 | Low |
| T18 | Wire emitter into ag build - ag build scans for changed .agscript files - Invokes parser then emitter for each changed file - Writes generated GDScript to .engine/generated/ - Reports parse/emit errors with AGS-spirit source locations | ag build on the test project produces GDScript files. Error messages reference AGS-spirit files and line numbers. | T05, T16 | Low |

MILESTONE 4 Room Node Implement the Room node type with logic geometry in the Godot editor

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T19 | Implement Room node type - C++ class AGSRoom extending Node3D - Register with Godot's ClassDB via module - Expose room_name property in editor inspector - Room appears in Add Node dialog under AGS3D category | Author can add an AGSRoom node to a Godot scene from the editor. Node visible in scene tree with correct icon. | T02 | Low |
| T20 | Implement WalkableSurface node type - C++ class AGSWalkableSurface extending StaticBody3D - Mesh automatically registered as navmesh source on room init - Visual: semi-transparent green overlay in editor, invisible at runtime | WalkableSurface mesh is automatically baked into the room navmesh on scene load. Character can navigate on it. | T19 | Med |
| T21 | Implement BlockerVolume node type - C++ class AGSBlockerVolume extending StaticBody3D with CollisionShape3D - Characters cannot enter the volume - Visual: semi-transparent red in editor, invisible at runtime | Character pathfinding correctly routes around BlockerVolume. Direct path through blocker is rejected. | T19 | Low |
| T22 | Implement named point placement - C++ class AGSPoint extending Node3D - point_name property exposed in inspector - Points visible as labelled gizmos in editor viewport - Points register themselves with parent AGSRoom on ready | AGSRoom.get_point("door_left") returns the correct world position at runtime. Adding a point in the editor makes it available by name in script. | T19 | Low |
| T23 | Implement TriggerRegion node type - C++ class AGSTriggerRegion extending Area3D - region_name property in inspector - Emits region_entered(character) and region_exited(character) signals - Registers with parent AGSRoom by name | When a character enters the volume, region_entered signal fires with the character reference. Signal is hookable from room script. | T19 | Low |
| T24 | Implement HotspotSurface node type - C++ class AGSHotspot extending Area3D with CollisionShape3D - hotspot_name property in inspector - Raycast from camera through mouse position hits hotspot CollisionShape - Emits hotspot_clicked(hotspot_name) signal to AGSRoom | Clicking on a HotspotSurface in a running game fires hotspot_clicked with the correct hotspot name. Room script can handle it. | T19 | Med |

MILESTONE 5 Character Node Implement the Character node with navigation and a blocking WalkTo call

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T25 | Implement Character node type - C++ class AGSCharacter extending CharacterBody3D - character_name property in inspector - Characters register with a global AGSRuntime singleton by name - Basic placeholder mesh (capsule) visible in editor | AGSCharacter appears in editor. AGSRuntime.get_character("player") returns the correct node at runtime. | T19 | Low |
| T26 | Integrate Godot NavigationAgent3D - AGSCharacter owns a NavigationAgent3D child - Navigation target set from AGSRoom named point positions - Character moves along navigation path using move_and_slide | Character navigates to a target point along the navmesh, correctly routing around BlockerVolumes. | T25, T20, T21 | Med |
| T27 | Implement WalkTo as a blocking GDScript function - GDScript method walk_to(point_name: String) on AGSCharacter - Looks up point position from parent room - Sets navigation target, awaits navigation_finished signal - Returns only after character reaches destination | await character.walk_to("door_left") blocks script execution until character arrives. Next script line runs only after arrival. | T26 | High |
| T28 | Implement character facing - face_to(point_name: String) method on AGSCharacter - Rotates character to face the named point position - Blocking: awaits rotation tween completion | character.face_to("window") correctly rotates the character toward the named point. | T27 | Low |
| T29 | Implement CharacterSpawnPoint node type - C++ class AGSSpawnPoint extending Node3D - spawn_character property: name of character to place here on room load - On room ready: finds named character in AGSRuntime, moves it to spawn position | Character appears at the correct spawn point when the room loads. No manual positioning in script needed. | T25 | Low |

MILESTONE 6 End-to-End Wiring Connect all systems so an AGS-spirit script drives a character in a room

This milestone is integration work. Each task here connects two previously isolated systems. Expect more debugging than implementation time.

| # | Task | Detail / Acceptance Criteria | Depends on | Risk |
| --- | --- | --- | --- | --- |
| T30 | Wire AGSScriptLanguage to generated GDScript - AGSScriptLanguage::load() triggers parse + emit for the corresponding .agscript file - Returns a Script resource backed by the generated GDScript - Godot attaches this script to the AGSRoom or AGSCharacter node normally | Attaching a .agscript file to an AGSRoom node in the editor triggers transpilation automatically. No manual build step needed from the editor. | T03, T18 | High |
| T31 | Implement AGSRuntime singleton - Autoload singleton registered by the agvm module - Tracks all AGSRoom and AGSCharacter nodes currently in the scene tree - Provides: get_room(name), get_character(name), get_point(room, point_name) - Initialised before any room script runs | From any script, AGSRuntime.get_character("player") and AGSRuntime.get_point("market", "door_left") return correct references. | T19, T25 | Med |
| T32 | Map AGS-spirit built-in names to runtime calls - Emitter maps character.WalkTo(point.x) to await AGSRuntime.get_character(name).walk_to(point_name) - Emitter maps room.Enter to AGSRuntime room_enter signal connection - Maintain a built-in name mapping table in the emitter | AGS-spirit standard library calls emit correct GDScript that invokes AGSRuntime methods. No hardcoded string literals in emitted code. | T15, T31 | High |
| T33 | Implement room script event binding - On AGSRoom ready: find attached .agscript-derived GDScript - Connect Godot signals to AGS-spirit event handler functions - Events: room_enter, room_exit, hotspot_clicked, region_entered, region_exited | function room_Enter() in .agscript fires correctly when the room loads. function hotspot_Interact("painting") fires when the painting hotspot is clicked. | T30, T32 | Med |
| T34 | Error message routing through source maps - GDScript runtime errors caught by AGSScriptLanguage error handler - Source map loaded for the offending GDScript file - GDScript line number translated to AGS-spirit file and line - Error displayed to author referencing AGS-spirit source | A runtime error in generated GDScript shows the author the correct .agscript file name and line number, not the generated GDScript path. | T17, T30 | Med |
| T35 | Build and run end-to-end prototype test - Author a minimal test project: one room, one character, one .agscript - Script: room_Enter walks player to named point, then faces a second point - ag build compiles the project - ag run launches and executes the script correctly | The character walks to the named point and faces the second point as scripted. No manual GDScript editing required. This task is the prototype success criterion. | T30–T35 | High |

# Summary

| Milestone | Tasks | Risk | Key Input | Done When |
| --- | --- | --- | --- | --- |
| M1 — Godot Fork Setup | T01–T05 | Low | Godot source | Fork builds, module loads, ag run works |
| M2 — AGS-Spirit Parser | T06–T12 | High | Grammar spec | AST produced for all grammar constructs |
| M3 — GDScript Emitter | T13–T18 | Med | AST | Valid GDScript emitted, source maps written |
| M4 — Room Node | T19–T24 | Med | Godot fork | Room with geometry and named points in editor |
| M5 — Character Node | T25–T29 | Med | Room node | Character navigates to named point |
| M6 — End-to-End | T30–T36 | High | All above | Script drives character. Prototype criterion met. |

Total: 36 tasks across 6 milestones. High-risk tasks: T09 (parser), T16 (await emit), T27 (blocking WalkTo), T30 (script language wiring), T32 (built-in name mapping), T36 (end-to-end). Address these first within each milestone — they are the tasks most likely to surface architectural problems.

AGS3D  —  Prototype Task List  —  Codename Document  —  2026